## 工作表1
Product Owner: Shuangning Liu
ID | Imp | Name | Notes | How to test | Workload | Member in charge
1 | 6 | User system | User login, Profile, email verification... | See if the basic social functions are complete | 2h | Du
2 | 3 | Main game logic for multiple users | more complicated rules | a perfect game logic without bugs | 2h | Yupeng
3 | 2 | Django channels: multiple users | Implement communications among multiple users and multiple groups | successfully communicate between multiple clients and the server | 9h | All 3 Members
4 | 4 | Data security | ensure the confidentiality among users and servers | see if the data transmitted could be easily caught by the client | 2h | Du
5 | 5 | Interactive UI | use javascript library to add animation and interactive displays | fluent flows withoud bugs | 2h | Shuangning
6 | 1 | High level design | Design the interactive process between multiple users movement and backend database | reasonable state change diagram guiding further implementation | 2h | Shuangning
7 | 7 | Deployment online | configure all the settings | Testing all the function online without bug | 2h | Du
8 | 2 | Main game logic: blind gambling | Every game, 2 users will be forced to pay blind bet | All need test in different cases, all possible number of players, all possible number of chips, specail cases for all in and draw and so on. | 1h | Du
9 | 2 | Main game logic: Raise | User can raise their bet according to some rules |  | 1h | Yupeng
10 | 2 | Main game logic: put/get chips | winner get all (specail cases for all in and draw) |  | 3h | Shuangning
11 | 2 | Main game logic: All in | In any time player can all in, and wait until the end of this game. |  | 3h | Yupeng
12 | 2 | Main game logic: Show card | When the game finished, winner can show his/her card |  | 1h | Yupeng