## 工作表1
Product Manager: Du Zhang
ID | Imp | Name | Notes | How to test | Workload | Member in charge
0 | 0 | Deployment | Complete deployment, bind to the domain name, conduct https validation | see if all the urls are directed to the correct page | 3h | Du
1 | 0 | Web socket | Enhance the robustness of web socket, solve the problem of automatically terminating after a while | ensure that web socket would not crash | 3h | Du
2 | 2 | UI refinement | Add animations, and interactive UI | Front end should display correctly for different users | 6h | Shuangning
3 | 1 | Game logic | Add all-in logic and fix previous bugs | Validate the correctness of the game logic in different situations | 6h | Yupeng and Du
4 | 0 | Multiple tables | Support multiple players play in different tables at the same time | Ensure bug-free when running different tables | 6h | Yupeng and Du
5 | 2 | Social network | Add user profile page, support chatting in the game and other function which can enhance user experience | Media and profiles won't mess up | 3h | All members
6 | 1 | Input validation | Validate all the requests sent to the server | See if the web server is able to handle all the requests | 2h | Yupeng
7 | 0 | UI design | New UI must collaborate with backend to let users create new tables easily | When add or delete a table, front end should display whether this table exists. In the backend, the table should be created or deleted correctly without a memory leak. | 3h | Shuangning