## 工作表1
Product Owner: Yupeng Zhang
ID | Imp | Name | Notes | How to test | Workload | Member in charge
0 | 2 | Survery on Django Channels | Learn how to make use of Django Channels https://channels.readthedocs.io/en/stable/ | Successful communication between server side and client side | 5hrs | All members
1 | 1 | Data models | Construct data models based on specification, including game_info, user_info, desk_info, card_info, chip_pool and game_ongoing | See if all the information required can be covered | 2hrs | Du Zhang
2 | 3 | Main Game Logic: Shuffle | This function generate a random sequence of 52 pork cards. Return the list of these port cards. | 1. Correctness: See if the list contains 52 unique pork cards. 2. Randomness: See if the result is independent from the time or other seed which can be observed and repeated. | 1hrs | Du Zhang
3 | 3 | Main Game Logic: License | This function pop the last card from the list of pork cards and return this card. | 1. See if it can be excuted successfully. 2. Edge Case: If the list is empty, return a error flag. | 1hrs | Du Zhang
4 | 3 | Main Game Logic: Compare | This function receive two list of cards, each contains 5 cards, it compare which combination will win the game according to the texas hold'en rules. | All cases and combinations will be contained in test cases. | 3hrs | Du Zhang
5 | 2 | Game UI Design | Design a game table, several operation panel and porker cards | Finished https://github.com/CMU-Web-Application-Development/Team319/blob/master/specification/wireframe/Texas%20Hold'em.pdf | 3hrs | Shuangning Liu
6 | 2 | Game UI Implementation | Draw the game UI using CSS, HTML5 or other web tools | Follow the previous design of wireframe | 3hrs | Shuangning Liu
7 | 3 | Client Event: Fold | The player give up this game and fold his/her card, send corresponding signal to the server. | See if the signal is successfully sent and received. | 2hrs | Shuangning Liu
8 | 3 | Client Event: Hold | The player choose to continue the game, send the signal to teh server. | See if the signal is successfully sent and received. | 2hrs | Shuangning Liu
9 | 3 | Server Event: License | Server call the license function to put an additional card in the table. | See if the player receive the card successfully and the card is removed from the list successfully. | 1hrs | Yupeng Zhang
10 | 3 | Server Event: Next | Server call the next player to move | See if the signal is sent and receive successgully. | 1hrs | Yupeng Zhang
11 | 3 | Server Event: Start | Server start the game, call Shuffle to get the card list, call license to put the initial 3 cards in the table, call license again to give each player 2 cards and decide the beginner player randomly. | See if all functions are in good conditions | 2hrs | Yupeng Zhang
12 | 3 | Server Event: End | When the game satisfy the following conditions, the game ends: 1. There is only one player in the table. 2. This is the last round of the game and all player have finished their move. Then the server call pick and compare funciton to decide who will win the game. | See if all functions are in good conditions | 2hrs | Yupeng Zhang